## Sheet1
Task | Planned Start date | Planned End date | Actual Start date | Actual End date | Status
Generate Unique ID | 2025-05-27 | 2025-05-27 |  |  | Pending
Commission Gateway via BLE | 2025-05-27 | 2025-05-27 |  |  | Pending
Save Config in LittleFS | 2025-05-27 | 2025-05-27 |  |  | Pending
Parse Config | 2025-05-27 | 2025-05-27 |  |  | Pending
Parse Model Code | 2025-05-28 | 2025-05-28 |  |  | Pending
Internet Connection Check | 2025-05-28 | 2025-05-28 |  |  | Pending
Ethernet with Static IP and DHCP | 2025-05-28 | 2025-05-28 |  |  | Pending
MQTT Connection | 2025-05-29 | 2025-05-30 |  |  | Pending
Modbus over Ethernet | 2025-05-29 | 2025-05-30 |  |  | Pending
Read(Group Wise)- and Publish Data (Modbus) | 2025-05-29 | 2025-05-30 |  |  | Pending
Subscribe and Write Data | 2025-05-29 | 2025-05-30 |  |  | Pending
Commands Lists | 2025-05-31 | 2025-05-31 |  |  | Pending
Send & Receive data via BLE | 2025-05-31 | 2025-05-31 |  |  | Pending
Gateway Status and State | 2025-05-31 | 2025-05-31 |  |  | Pending
Gateway Diagnostics to Mobile Application | 2025-05-31 | 2025-05-31 |  |  | Pending
Put Required Hardcoded Settings | 2025-06-01 | 2025-06-01 |  |  | Pending
Macro and Condition Driven Dynamic Code with Flags | 2025-06-01 | 2025-06-01 |  |  | Pending
Store data into Sd card | 2025-06-02 | 2025-06-02 |  |  | Pending
Update Config + Compare Model Code | 2025-06-02 | 2025-06-02 |  |  | Pending
Data Integrity with CRC | 2025-06-03 | 2025-06-03 |  |  | Pending
Compression and Decompression | 2025-06-03 | 2025-06-03 |  |  | Pending
OTA Methods | 2025-06-03 | 2025-06-04 |  |  | Pending